## Sheet1
Working Process
Project Lead : Mr.Natchapol Patamawisut (Bank) | [10 empty] | Start Project : 1/3/2021 | [11 empty] | Done
Secretary : Ms.Natchariya Wongamnuayporn (Kao) | [10 empty] | Finish Project : 31/5/2021 | [11 empty] | In Process
Late
Scurm Master : Kao & Project Manager : Bank | [22 empty] | Not assign
Work description | Assign to | Start Date | 2021-03-01 |  |  |  | 2021-04-01 |  |  |  | 2021-05-01 |  |  |  | 2021-06-01 |  |  |  | Percent (%) | Finish Date | Period Days | Note
|  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Sprint1 : Conceptual design (1/3/2021 - 31/3/2021)
Get requirement | All member | 2021-03-01 | [16 empty] | 100% | 2021-03-03 | 2 | bar: 2021-03-01 1
Midterm Exam | All member | 2021-03-08 | [16 empty] | NA | 2021-03-12 | 5 | Midterm Exam | bar: 2021-03-01 2
Requirement Document | Kao,Bank | 2021-03-15 | [16 empty] | 100% | 2021-03-20 | 5 | bar: 2021-03-01 3
Meeting | All member | 2021-03-27 | [16 empty] | 100% | 2021-03-28 | 1 | bar: 2021-03-01 4
Presentation | All member | 2021-03-31 | [16 empty] | 100% | 2021-03-31 | 1 | End Sprint 1 | bar: 2021-03-01 4 to 2021-06-01 4
Sprint2 : System design (31/3/2021 - 26/4/2021)
Meeting | All member | 2021-03-31 | [16 empty] | 100% | 2021-03-31 | 1 | bar: 2021-03-01 4
Create IaC | Eye | 2021-03-31 | [16 empty] | 100% | I : 4/4/2021 ( II : 10/4/2021)( III : 18/4/2021)( IV : 21/4/2021)( V : 25/4/2021 | ~ 19 | Blob Storage , PostgreSQL and Data warehouse | bar: 2021-04-01 1 to 2021-04-01 3
Programming | Bank | 2021-03-31 | [16 empty] | 100% | 2021-04-04 | 5 | Manage data to match the data model | bar: 2021-04-01 1
Demo Visualization | Kao,New | 2021-03-31 | [16 empty] | 100% | 2021-04-04 | 5 | bar: 2021-04-01 1
Demo Docker | Fuze | 2021-03-31 | [16 empty] | 100% | 2021-04-05 | 6 | bar: 2021-04-01 1
Meeting | All member | 2021-04-04 | [16 empty] | 100% | 2021-04-04 | 1 | Update work | bar: 2021-04-01 1
Extract and load Data | Fuze | 2021-04-05 | [16 empty] | 100% | 2021-04-21 | 16 | Upload & Download | bar: 2021-04-01 2 to 2021-04-01 3
Visualization | Kao,New | 2021-04-05 | [16 empty] | 100% | 2021-04-18 | 13 | Dashboard | bar: 2021-04-01 2 to 2021-04-01 3
Power BI POST request API | Kao | 12/4/021 | [16 empty] | 100% | 2021-04-22 | 10 | bar: 2021-04-01 2 to 2021-04-01 3
Machine Learning | Bank | 2021-04-05 | [16 empty] | 100% | 2021-04-18 | 13 | bar: 2021-04-01 2 to 2021-04-01 3
Testing & Report | Kao,Bank | 2021-04-19 | [16 empty] | 100% | 2021-04-20 | 1 | bar: 2021-04-01 3
Presentation | All member | 2021-04-26 | [16 empty] | 100% | 2021-04-26 | 1 | End Sprint 2 | bar: 2021-04-01 4
Sprint3 : Implement & Deployment (26/4/2021 - 10/5/2021)
Meetings | All member | 2021-04-26 | [16 empty] | 100% | 2021-04-26 | 1 | bar: 2021-04-01 4
New Model | Bank | 2021-05-02 | [16 empty] | 100% | 2021-05-09 | 7 | bar: 2021-04-01 4 to 2021-05-01 1
Airflow | Bank | 2021-04-26 | [16 empty] | 100% | 2021-05-02 | 6 | Automate workflow | bar: 2021-04-01 4 to 2021-05-01 1
Deploy Airflow | Fuze | 2021-05-02 | [16 empty] | 100% | 2021-05-09 | 7 | bar: 2021-04-01 4 to 2021-05-01 1
Data Factories | Kao | 2021-05-02 | [16 empty] | 100% | 2021-05-11 | 9 | Transform Data | bar: 2021-04-01 4 to 2021-05-01 1
Data Label | Eye | 2021-05-02 | [16 empty] | 100% | 2021-05-07 | 5 | bar: 2021-04-01 4 to 2021-05-01 1
Testing | Kao,Bank | 2021-05-04 | [16 empty] | 100% | 2021-05-11 | 7 | bar: 2021-05-01 1
End Sprint 3 | All member | 2021-05-10 | [16 empty] | 100% | 2021-05-10 | 1 | End Sprint 3 | bar: 2021-05-01 1
Sprint 4 : Testing (10/5/2021 - 7/6/2021)
Meetings | All member | 2021-05-12 | [16 empty] | 100% | 2021-05-12 | 1 | bar: 2021-05-01 1
Testing Model | Bank | 2021-05-12 | [16 empty] | 100% | 2021-05-20 | 8 | bar: 2021-05-01 1 to 2021-05-01 2
Testing Pipeline | Eye | 2021-05-12 | [16 empty] | 100% | 2021-05-20 | 8 | bar: 2021-05-01 1 to 2021-05-01 2
Testing Infrastructure | Fuze | 2021-05-12 | [16 empty] | 100% | 2021-05-20 | 8 | bar: 2021-05-01 1 to 2021-05-01 2
Testing Dashboard | New | 2021-05-12 | [16 empty] | 100% | 2021-05-20 | 8 | bar: 2021-05-01 1 to 2021-05-01 2
Testing & Report | Kao,Bank | 2021-05-19 | [16 empty] | 100% | 2021-05-21 | 3 | All testing & Report | bar: 2021-05-01 3 to 2021-05-01 4
Final Presentation | All member | 2021-06-05 | [16 empty] | 100% | 2021-06-05 | 1 | End Sprint 4 | bar: 2021-06-01 1 to 2021-06-01 2